ENG MEETING ORGANISATION
 This is not a fixed methodology but a suggestion of practical tools to organise RTF meetings. It departs from the idea that the organisation of these meetings is shared between a local group that takes care of logistics and a group taking care of content
Questions on Location / local group
- amount of places for meetings, amount of sleeping spaces - available spaces: kitchen, welcome space, meeting spaces, party space, resting area, dormitories, outside - material and financial needs of hosting space - procurement of materials and food - availability of internet, printing, phone, … - local issues, actions …?
Before and during assembly - clear welcome of the participants - collective review (daily?): group guidelines on living and meeting conducts, collective time, timing of meetings, content - regular synthesis on decisions and meeting issues - reminders on practical stuff: collective tasks, money, … - attentiveness to minutes
Preparation of content in order of priority - agreement on location and meeting objectives in assembly and/or on Carrots - call-out on European list to organisers, for content, themes - announcement on the EU list on dates, location, issues - inscription of motivated people on carrots - if needed: questionnaires, call-outs to fine tune themes - first draft of a general program
Communication - address the EU list and/or local lists and/or external - send first general mailing several months in advance - send mail reminder ( 3 months prior) - put information on website - send practical mail 1 month prior: how to get there, food, program, needs
Preparation in situ - local group: prepare procurement (orders, harvest, stock) - local group: find materials, install the space - content group: synthesis of intervention proposals and discussion issues, advice on the program - content group: preparing days programs, plannings, daily life, task lists - both groups: preparing logistics and meetings views - both groups: prepare visits, volontary work on site, contacts with outsiders
After the meetings - cleaning up - share/distribute rests, stuff,… - gather meeting minutes with Bulletin group - thank you mailing and final state of affairs on EU list - announce follow-up, calender,etc…